## Program
Program | Service Campaign Rollout
Start Date | 2027-01-04
Status Date | 2027-04-08

## Tasks
ID | Task | Workstream | Owner | Predecessors | Optimistic (d) | Most Likely (d) | Pessimistic (d) | Budget | % Complete | Actual Cost
T1 | Root-cause analysis | Engineering | E. Novak |  | 13 | 15 | 30 | 30000 | 100% | 27416
T2 | Supplier quote | Parts & Supply | G. Kim | T1 | 3 | 5 | 10 | 4000 | 100% | 4234
T3 | Repair procedure draft | Service Ops | B. Chen | T1+1, T2 | 9 | 12 | 20 | 18000 | 100% | 20176
T4 | Regulatory filing | Compliance | G. Kim | T2+1, T3+1 | 7 | 10 | 14 | 15000 | 100% | 16391
T5 | FAQ and scripts | Customer Comms | F. Haddad | T1 | 1 | 2 | 4 | 3000 | 100% | 2778
T6 | Fix design review | Engineering | G. Kim | T2, T3 | 0 | 0 | 0 | 0 | 100% | 0
T7 | Tooling change | Parts & Supply | D. Patel | T5 | 0 | 0 | 0 | 0 | 100% | 0
T8 | Technician training | Service Ops | F. Haddad | T7+2 | 12 | 15 | 29 | 18000 | 100% | 17432
T9 | Defect report submission | Compliance | G. Kim | T2 | 7 | 10 | 18 | 8000 | 100% | 9660
T10 | In-app notification | Customer Comms | B. Chen | T6 | 4 | 5 | 8 | 7500 | 100% | 7269
T11 | Software update build | Engineering | D. Patel | T4, T5, T6+1 | 6 | 9 | 14 | 18000 | 100% | 19062
T12 | Parts PPAP | Parts & Supply | E. Novak | T5+2 | 1 | 2 | 4 | 1600 | 100% | 1860
T13 | Service bulletin | Service Ops | D. Patel | T2+2, T6 | 12 | 15 | 20 | 12000 | 100% | 13771
T14 | Owner notification letter | Compliance | B. Chen | T4, T8+2, T11+2 | 7 | 10 | 16 | 8000 | 100% | 8750
T15 | Call center briefing | Customer Comms | F. Haddad | T3+1, T13, T14 | 4 | 6 | 9 | 4800 | 31% | 1582
T16 | Validation testing | Engineering | B. Chen | T5+1, T8, T15 | 6 | 9 | 16 | 13500 | 0% | 0
T17 | Initial parts build | Parts & Supply | F. Haddad | T8+1, T11+2, T14+2 | 2 | 4 | 8 | 8000 | 0% | 0
T18 | Labor time study | Service Ops | G. Kim | T7+2, T16+1 | 0 | 0 | 0 | 0 | 0% | 0
T19 | Quarterly status report | Compliance | C. Okafor | T7, T15 | 3 | 4 | 6 | 8000 | 0% | 0
T20 | Dealer communication | Customer Comms | G. Kim | T12, T13+2, T18 | 6 | 8 | 14 | 16000 | 0% | 0
T21 | Field test | Engineering | B. Chen | T15+2, T16+2, T20 | 4 | 7 | 11 | 10500 | 0% | 0
T22 | Distribution to service centers | Parts & Supply | F. Haddad | T18+1, T20+1 | 5 | 6 | 13 | 7200 | 0% | 0
T23 | Mobile service scheduling | Service Ops | A. Rivera | T18 | 3 | 4 | 8 | 8000 | 0% | 0
T24 | Remedy adequacy review | Compliance | C. Okafor | T13, T17, T20 | 6 | 7 | 12 | 5600 | 0% | 0
T25 | Customer survey | Customer Comms | G. Kim | T17, T20+1 | 2 | 2 | 4 | 3000 | 0% | 0
T26 | Design release | Engineering | D. Patel | T15+1, T24+2, T25+2 | 6 | 9 | 11 | 7200 | 0% | 0
T27 | Safety stock build | Parts & Supply | C. Okafor | T18+1 | 4 | 5 | 6 | 7500 | 0% | 0
T28 | Center readiness check | Service Ops | E. Novak | T17 | 0 | 0 | 0 | 0 | 0% | 0
T29 | Records audit | Compliance | D. Patel | T22, T24, T26 | 2 | 4 | 8 | 8000 | 0% | 0
T30 | Website update | Customer Comms | E. Novak | T18+2, T26, T29 | 3 | 3 | 5 | 6000 | 0% | 0
T31 | Root-cause analysis (wave 2) | Engineering | B. Chen | T22+1, T27+1 | 6 | 8 | 15 | 9600 | 0% | 0
T32 | Supplier quote (wave 2) | Parts & Supply | A. Rivera | T21, T28 | 8 | 10 | 15 | 15000 | 0% | 0
T33 | Repair procedure draft (wave 2) | Service Ops | E. Novak | T31 | 9 | 14 | 26 | 11200 | 0% | 0
T34 | Regulatory filing (wave 2) | Compliance | G. Kim | T28 | 10 | 15 | 25 | 22500 | 0% | 0
T35 | FAQ and scripts (wave 2) | Customer Comms | F. Haddad | T24+2, T30 | 8 | 11 | 17 | 16500 | 0% | 0
T36 | Fix design review (wave 2) | Engineering | F. Haddad | T26, T27 | 4 | 6 | 12 | 9000 | 0% | 0
T37 | Tooling change (wave 2) | Parts & Supply | F. Haddad | T25+2, T26, T27 | 2 | 3 | 6 | 3600 | 0% | 0
T38 | Technician training (wave 2) | Service Ops | D. Patel | T29+2, T34, T35 | 6 | 8 | 15 | 6400 | 0% | 0
T39 | Defect report submission (wave 2) | Compliance | C. Okafor | T27, T35+1 | 4 | 6 | 10 | 12000 | 0% | 0
T40 | In-app notification (wave 2) | Customer Comms | A. Rivera | T30, T31, T36+1 | 6 | 9 | 18 | 10800 | 0% | 0
T41 | Software update build (wave 2) | Engineering | C. Okafor | T30+2, T37 | 12 | 15 | 24 | 22500 | 0% | 0
T42 | Parts PPAP (wave 2) | Parts & Supply | B. Chen | T32+2 | 10 | 12 | 20 | 14400 | 0% | 0
T43 | Service bulletin (wave 2) | Service Ops | C. Okafor | T35, T36+2 | 2 | 3 | 6 | 6000 | 0% | 0
T44 | Owner notification letter (wave 2) | Compliance | A. Rivera | T32+2, T41 | 6 | 7 | 15 | 5600 | 0% | 0
T45 | Call center briefing (wave 2) | Customer Comms | A. Rivera | T40, T43+2 | 7 | 8 | 11 | 6400 | 0% | 0
T46 | Validation testing (wave 2) | Engineering | F. Haddad | T40 | 9 | 14 | 30 | 28000 | 0% | 0
T47 | Initial parts build (wave 2) | Parts & Supply | D. Patel | T45+1 | 3 | 5 | 8 | 6000 | 0% | 0
T48 | Labor time study (wave 2) | Service Ops | A. Rivera | T41+1 | 11 | 12 | 25 | 14400 | 0% | 0
T49 | Quarterly status report (wave 2) | Compliance | B. Chen | T37, T39, T43 | 0 | 0 | 0 | 0 | 0% | 0
T50 | Dealer communication (wave 2) | Customer Comms | B. Chen | T44+2 | 12 | 15 | 22 | 18000 | 0% | 0
T51 | Field test (wave 2) | Engineering | B. Chen | T42, T47+1 | 7 | 10 | 20 | 20000 | 0% | 0
T52 | Distribution to service centers (wave 2) | Parts & Supply | G. Kim | T41, T43 | 10 | 15 | 33 | 30000 | 0% | 0
T53 | Mobile service scheduling (wave 2) | Service Ops | G. Kim | T49 | 6 | 9 | 14 | 10800 | 0% | 0
T54 | Remedy adequacy review (wave 2) | Compliance | G. Kim | T42, T52+2 | 7 | 8 | 16 | 16000 | 0% | 0
T55 | Customer survey (wave 2) | Customer Comms | C. Okafor | T46+2, T50+1, T53 | 5 | 6 | 8 | 12000 | 0% | 0
T56 | Design release (wave 2) | Engineering | D. Patel | T47, T49, T54 | 8 | 9 | 16 | 18000 | 0% | 0
T57 | Safety stock build (wave 2) | Parts & Supply | B. Chen | T48 | 10 | 13 | 28 | 15600 | 0% | 0
T58 | Center readiness check (wave 2) | Service Ops | C. Okafor | T50 | 8 | 11 | 21 | 8800 | 0% | 0
T59 | Records audit (wave 2) | Compliance | E. Novak | T53 | 10 | 12 | 15 | 24000 | 0% | 0
T60 | Website update (wave 2) | Customer Comms | A. Rivera | T52, T53, T59+2 | 9 | 12 | 21 | 24000 | 0% | 0

## Risks
ID | Risk | Owner | Probability (1-5) | Impact (1-5) | Mitigation
R1 | Supplier capacity shortfall delays parts | A. Rivera | 2 | 5 | Qualify second source; weekly supply call
R2 | Regulator requests additional remedy data | B. Chen | 2 | 2 | Pre-brief regulator; hold test data package
R3 | Software update fails field validation | C. Okafor | 3 | 3 | Staged rollout with rollback plan
R4 | Technician training completion below target | D. Patel | 1 | 1 | Add remote sessions; track by center
R5 | Owner contact data incomplete | E. Novak | 5 | 3 | Cross-match registration data; mail fallback
R6 | Parts quality escape at first build | F. Haddad | 2 | 5 | 100% inspection on first lot
R7 | Service center capacity constrained | G. Kim | 3 | 5 | Extended hours; mobile service
R8 | Scope grows to additional model years | A. Rivera | 1 | 3 | Pre-scope VIN ranges with engineering
R9 | Labor time underestimated | B. Chen | 5 | 4 | Time study at pilot centers before release
R10 | Translation of notices delayed | C. Okafor | 4 | 3 | Start localisation from draft text
R11 | Key engineer unavailable | D. Patel | 5 | 2 | Named backup on each critical task
R12 | Logistics disruption at port | E. Novak | 4 | 3 | Pre-position stock regionally

## Holidays
Holiday
2027-01-18
2027-02-15
2027-05-31
2027-07-05
2027-09-06
2027-11-25
2027-12-24